## Sheet1
Project | Development of DSE-ERP
Module Already Done
HR Related
Sl No | Module Name | Status | Remarks
1 | Basic Administration and Dashboard | Done
2 | Leave Management System | done
3 | Employee Management | done
4 | Circular Management | done
5 | EL Encashment Module | done
6 | KPI And PA Automation | Ready for UAT and Deployement | Need update as per UAT changes
7 | PayRoll Management System | Ready for Go-Live | Need instruction by management to use
8 | Income Tax Management | Done
9 | Travel Management | To be done
10 | Provident Fund Management | Done
11 | Gratuity Management | Done
12 | Attendance Manangment | Done
13 | Duty Roster Management | Done
14 | Loan and Advance Management | done
Finance ,Procurement related
Sl No | Module Name | Status | Remarks
15 | Bank Guarantee Management | Done
16 | Inventory and Store Management | done
17 | Asset Management | Done | Need integration with Accounting and procurement system
18 | Meeting Management System | Done | Prepare agenda, Approval, Create minutes and task assignment
Running Projects
Sl No | Module Name | Features
1 | Automation of Budget management | • Online budget submission • Online budget Approval • Real-time update of free balance • Ensuring budget governance
2 | Automation of MRF, Procurement | Online MRF submission Online review/approval of MRF Automation of Tender/Regular purchase process Receiving process automation with unique GRN Detailed Supplier/Subcontractor/Service Provider database Vendor evaluation option MIS for vendor evaluation based on quality, price & delivery time. Reporting requirement for departmental monitoring & management
Phase of implementation
Automation of Budget management
| Steps |  | Time Line
| 1. Prepare Budget Chart of accounts | Phase-1 | By 30-Jan-2023
2. Request Departmental Budget
Request General Budget(Income/Expenditure)
Request for Departmental Project
Request Item wise Budget
3. Verification by Dept/Division Head
4. Review by Finance Division
5. Review by Management
6. Review by ARC Committee/Board
7. Approve by Board
8. Request for Budget Shifting
Review /approval for shifting
9. Budget Dashboard
10. Search and Reporting
Dynamic Budget Variance Report
Account Type wise report
Department/Division wise report
Smart searching
| 11. Integration with Procurement System | Phase-2 | By 30-Jun-2023 when budget will be ready to use for the fiscal year 2023-2024
Automation of MRF, Procurement
| 1. Requisition management for procurement | Phase-3
a. Material requisition (MRF) rose by different dept.
b. Justification/ actual need assessment of the requisition by the departmental & divisional head
| c. Examining the budget availability by the budget section with the requisition raised by a different department |  | By 30-Mar-2023
d. Administrative approval by DSE management as per Procurement Manual and General Financial Guideline 2016 of DSE and send to Common Service Dept.
| 2. Regular & Tender purchase process | Phase-6
| a. Approval Process of procurement activities by Common Services Dept. |  | By 30-Dec-2023
b. Purchase order processing.
c. Prepare tender process & selection of vendor process
d. RFQ/RFP Management
e. Comparative statements/single vendor justification
f. Purchase order entry with item details and other details like taxes, and discounts. Extra charges like freight, C&F.
g. PO authorization.
h. PO amendments with complete amendment history
i. Multiple indents for multiple items in a single PO
j. Flexibility to generate Purchase orders in domestic and foreign currency.
| 3. Receiving Process | Phase-4
| a. Quality inspection of goods receiving (GRN) |  | By 30-Jun-2023
b. Advance adjustments.
c. Purchase bill with updating of GL and purchase book.
d. Multiple delivery schedules.
e. GRN management
f. Invoice Verification
| 4. Detailed Supplier/Subcontractor/Service Provider database | Phase-5 | By 30-Jun-2023
5. Vendor evaluation option
6. MIS for vendor evaluation based on quality, price & delivery time.
7. Reporting requirement for departmental monitoring & management
| Integration of asset management system with MRF process | Phase-6 | By 30-Dec-2023