## Task List
No | Project/Task | Task Type | Tasks | Modules (ongoing/Existing futures) | Frequency | Time Consumed Daily By Kamruzzaman EIN-52 Senior Manager | Time Consumed Daily By Abdul Kader EIN-94 Senior Manager | Time Consumed Daily By Golam Kibria EIN-108 Manager | Time Consumed Daily By Kamrul Hasan EIN-490 Senior Executive | Time Consumed Daily By Mahsin Kabir EIN-493 Senior Executive | Time Consumed Daily By Saiful Islam EIN-496 Senior Executive
1 | Electronic Subscription System (ESS) User group : TREC, Companies, DSE | Development | Requirement Gathering & Analysis | Application, Validation and allotment of righ offers for preferenced shares, Implment amendment of public issue rules | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Review analyzed requirements |  | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Software Architecture Design |  | On demand | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | User Interface (UI/UX) Design |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Implementation (Coding/Development) |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Manual Testing |  | Daily | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | Fixing bugs in any during UAT/MOCK |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | Final deployment with data migration(if any) |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | Bug Fixing |  | On demand | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | Application Deployment |  | On demand | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | File Server Monitoring & Backup Management |  | Daily | 0.2 | 0 | 0.2 | 0.2 | 0 | 0
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0 | 0.1 | 0.1 | 0 | 0
|  | Operation | User Management |  | On demand | 0 | 0 | 0.1 | 0.1 | 0 | 0
|  |  | Role Based Access Management |  | On demand | 0 | 0 | 0.1 | 0.1 | 0 | 0
2 | Clearing and Settlement System (CNS) User group : TREC, DSE | Development | Requirement Gathering & Analysis | Charge module (tax on accrued interest for G-Sec trades) Manage schedule of record dates and disseminate the same to brokers through CNS | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Review analyzed requirements |  | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  |  | Software Architecture Design |  | On demand | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | User Interface (UI/UX) Design |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Implementation (Coding/Development) |  | Daily | 0 | 0.3 | 0 | 0 | 0 | 0
|  |  | Manual Testing |  | Daily | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  |  | Final deployment with data migration(if any) |  | On demand | 0 | 0.2 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0 | 0.1 | 0.2 | 0.2 | 0 | 0
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0.1 | 0.2 | 0.2 | 0 | 0
|  |  | Bug Fixing |  | On demand | 0 | 0.1 | 0.2 | 0.2 | 0 | 0
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0.1 | 0.2 | 0.2 | 0 | 0
|  |  | Application Deployment |  | On demand | 0 | 0.1 | 0.2 | 0.2 | 0 | 0
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0.1 | 0.1 | 0.1 | 0 | 0
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0.1 | 0.1 | 0.1 | 0 | 0
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0.1 | 0.1 | 0.1 | 0 | 0
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0.1 | 0.1 | 0.1 | 0 | 0
|  | Operation | User and Access Management - User account administration (Add, Edit, Inactivate) - User IP management (Add, Remove) - Password Change | Existing User Module | On demand | 0 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1
|  |  | Prepare and dissemination of various reports as per requirements of conern departments | Existing Trade Module | On demand | 0 | 0.1 | 0.5 | 0 | 0 | 0
|  |  | Corporate Actions Management - Adding new instruments - Spot settings - Group changes - Instrument renaming - Instrument delisting - Trade code changes for instruments - Holiday operations - Handling fund shortages - Handling share shortages - Member code changes - Adding new members | Existing Administrative Module | Daily | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
|  |  | Trade File generation -Market File generation -Pay-in File generation -Payout File generation -Government Securities (GSec) file generation | Existing Trade Module | Daily | 0 | 0 | 0 | 0.25 | 0.25 | 0.25
|  |  | CDBL Operations - Market File processing -Pay-in File processing - Payout File processing - Government Securities (GSec) file processing | CDBL Software | Daily | 0 | 0 | 0 | 0.25 | 0.25 | 0.25
|  |  | Maintain the Operational History in ERP | DSE ERP Info Collection Module | Daily | 0 | 0 | 0 | 0.25 | 0.25 | 0.25
|  |  | Veify Operational History in ERP | DSE ERP Info Collection Module | Daily | 0.1 | 0 | 0.3 | 0 | 0 | 0
3 | DSE ERP User group : DSE, Board of Directors | Development | Requirement Gathering & Analysis | Meeting Management Module Intern Management Module Smart Dashboard for HR HRM-Loan module Migrate the Action Management Module from DSS to ERP and Integrating it with Meeting Management. | On demand | 0.2 | 0 | 0 | 0 | 0.2 | 0.1
|  |  | Review analyzed requirements |  | On demand | 0.2 | 0 | 0 | 0 | 0.2 | 0.1
|  |  | Documentation (Functional ,Technical Specs & Official) |  | On demand | 0.2 | 0 | 0 | 0 | 0.2 | 0.1
|  |  | Software Architecture Design |  | On demand | 0.5 | 0 | 0 | 0 | 0.2 | 0.1
|  |  | Database Design (Schema, Optimization, Migration Planning) |  | Daily | 0.5 | 0 | 0 | 0 | 0.5 | 0.1
|  |  | User Interface (UI/UX) Design |  | Daily | 0.5 | 0 | 0 | 0 | 0.5 | 0.25
|  |  | Implementation (Coding/Development) |  | Daily | 0.5 | 0 | 0 | 0 | 0.5 | 0.25
|  |  | Manual Testing |  | Daily | 0.2 | 0 | 0 | 0 | 0.5 | 0.25
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  |  | Fixing bugs in any during UAT/Mock |  | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  |  | Final deployment with data migration(if any) |  | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  |  | User Training & Knowledge Transfe |  | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  |  | Bug Fixing |  | On demand | 0.2 | 0 | 0 | 0 | 0.4 | 0.1
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | Application Deployment |  | On demand | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | File Server Monitoring & Backup Management |  | Daily | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0.2 | 0 | 0 | 0 | 0.3 | 0.1
|  | Operation | User Management |  | On demand | 0.1 | 0 | 0 | 0 | 0.3 | 0.1
|  |  | Role Based Access Management |  | On demand | 0.1 | 0 | 0 | 0 | 0.3 | 0.1
4 | Trec Management System (TMS) User group : DSE | Development | Requirement Gathering & Analysis | Facilitating TREC to View Their Information Rearchitech User Management Module Dashboard for TREC Company Basic Information Key contact persons TREC Info, Broker Info, Dealer Info Authorized Representative Approved Offices Workstations Board of Directors of the Company Shareholders of the Company | On demand | 0.2 | 0 | 0.2 | 0 | 0.3 | 0.2
|  |  | Review analyzed requirements |  | On demand | 0.2 | 0 | 0.2 | 0 | 0.2 | 0.2
|  |  | Documentation (Functional ,Technical Specs & Official) |  | On demand | 0.2 | 0 | 0.2 | 0 | 0.2 | 0.2
|  |  | Software Architecture Design |  | On demand | 0.2 | 0 | 0.2 | 0 | 0.2 | 0.2
|  |  | Database Design (Schema, Optimization, Migration Planning) |  | Daily | 0.5 | 0 | 0.2 | 0 | 0 | 0.5
|  |  | User Interface (UI/UX) Design |  | Daily | 0 | 0 | 0.3 | 0 | 0 | 0.5
|  |  | Implementation (Coding/Development) |  | Daily | 0 | 0 | 0.3 | 0 | 0 | 0.5
|  |  | Manual Testing |  | Daily | 0 | 0 | 0.3 | 0 | 0 | 0.5
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | Fixing bugs in any during UAT/Mock |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | Final deployment with data migration(if any) |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | Bug Fixing |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | Application Deployment |  | On demand | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  | Operation | User and Access Management |  | On demand | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  |  | Role Based Access Management |  | On demand | 0 | 0 | 0.1 | 0 | 0 | 0.1
5 | Job Portal User group : DSE, Outsider | Development | Requirement Gathering & Analysis | No development in progress /Change Request |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Review analyzed requirements |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Software Architecture Design |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | User Interface (UI/UX) Design |  |  | 0 | 0 | 0 | 0.3 | 0 | 0
|  |  | Implementation (Coding/Development) |  |  | 0 | 0 | 0 | 0.3 | 0 | 0
|  |  | Manual Testing |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  |  | 0 | 0 | 0 | 0.1 | 0 | 0
|  |  | Final deployment with data migration(if any) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0.05 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | User Training & Knowledge Transfer |  | On demand | 0.05 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | Bug Fixing |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | Application Deployment |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  | Operation | User and Access Management |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
|  |  | Role Based Access Management |  | On demand | 0 | 0.05 | 0 | 0.05 | 0 | 0
6 | Centralized Information Management System (CIMS) User group : DSE | Development | Requirement Gathering & Analysis | AGM,EGM,Rights, Treasury bond, Corporate bond Financials data Data integration with various data source Historical excel data migration with validationss | On demand | 0.2 | 0.2 | 0 | 0.2 | 0 | 0
|  |  | Review analyzed requirements |  | On demand | 0.2 | 0.2 | 0 | 0.2 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  | On demand | 0.2 | 0.2 | 0 | 0.2 | 0 | 0
|  |  | Software Architecture Design |  | On demand | 0.2 | 0.2 | 0 | 0.2 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  | On demand | 0.25 | 0.25 | 0 | 0.5 | 0 | 0
|  |  | User Interface (UI/UX) Design |  | Daily | 0 | 0.25 | 0 | 0.5 | 0 | 0
|  |  | Implementation (Coding/Development) |  | Daily | 0 | 0.25 | 0 | 0.5 | 0 | 0
|  |  | Manual Testing |  | Daily | 0 | 0.25 | 0 | 0.5 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  | On demand | 0 | 0.1 | 0 | 0.2 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  | On demand | 0 | 0.1 | 0 | 0.2 | 0 | 0
|  |  | Final deployment with data migration(if any) |  | On demand | 0 | 0.1 | 0 | 0.1 | 0 | 0
|  | Support | User Support and Issue Resolution | No Existing Module | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Bug Fixing |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Application Deployment |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0 | 0 | 0 | 0 | 0
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0 | 0 | 0 | 0 | 0
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  | Operation | User and Access Management |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Role Based Access Management |  | On demand | 0 | 0 | 0 | 0 | 0 | 0
7 | Offline Surveillance User group : DSE | Development | Requirement Gathering & Analysis | No development in progress |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Review analyzed requirements |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Software Architecture Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Interface (UI/UX) Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implementation (Coding/Development) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Manual Testing |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final deployment with data migration(if any) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | All Existing Module |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | User Training & Knowledge Transfer |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | Bug Fixing |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  | Manitence | Performance Optimization (Code, Database, Queries) |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | Application Deployment |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | File Server Monitoring & Backup Management |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | System Optimization (Server & Application Environment) |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  | Operation | User and Access Management |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
|  |  | Role Based Access Management |  |  | 0 | 0.05 | 0.05 | 0 | 0 | 0
8 | Advance Income Tax (AIT) User group : DSE | Development | Requirement Gathering & Analysis | Legacy and unmanageable project; planning required for migration to CNS/CIMS. |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Review analyzed requirements |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Software Architecture Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Interface (UI/UX) Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implementation (Coding/Development) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Manual Testing |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final deployment with data migration(if any) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | All Existing Modules | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Bug Fixing |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Application Deployment |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  | Operation | User and Access Management |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Role Based Access Management |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
9 | App Support User group : DSE | Development | Requirement Gathering & Analysis | Legacy and unmanageable project. Migration to ERP/TMS is required. Source code is not available |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Review analyzed requirements |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Documentation (Functional ,Technical Specs & Official) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Software Architecture Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Database Design (Schema, Optimization, Migration Planning) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Interface (UI/UX) Design |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implementation (Coding/Development) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Manual Testing |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | UAT/MOCK Execution (Staging Environment Setup & Testing) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fixing bugs in any during UAT/Mock |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final deployment with data migration(if any) |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Support | User Support and Issue Resolution | Existing Action Management Module | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | User Training & Knowledge Transfer |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Bug Fixing |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  | Manitence | Performance Optimization (Code, Database, Queries) |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Application Deployment |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Database Maintenance (UAT & Live) – Backup, Monitoring |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Server Maintenance – Health Checks, SSL, Storage Monitoring. |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | File Server Monitoring & Backup Management |  | Daily | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | System Optimization (Server & Application Environment) |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  | Operation | User and Access Management |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
|  |  | Role Based Access Management |  | On demand | 0 | 0 | 0.05 | 0 | 0 | 0.05
10 | Additional Contributions | Involvment in various teams like technical evaluation, Vendor Enlistment , scrutinize IT related tender documents,Citizen's Charter etc. |  |  | On demand | 0.3 | 0.2 | 0.05 | 0.05 | 0.05 | 0.05
|  | ESS management team,EPF trustee, GPF trustee |  |  | On demand | 0.2 | 0.2 | 0 | 0 | 0 | 0
|  | Participate in brainstorming sessions, technical awareness programs, and problem-solving workshops with both team members and management. |  |  | On demand | 0.3 | 0.2 | 0.05 | 0.05 | 0.05 | 0.05
|  | Various task centric teams |  |  | On demand | 0.3 | 0.2 | 0.05 | 0.05 | 0.05 | 0.05
[6 empty] | 10.45 | 10.3 | 10.1 | 10.05 | 10 | 10.15

## On-going Projects
Ongoing projects
| Project Name | Possible Deadline | Remarks | Responsiblily | Supervison
1 | Centralize Information Management(CIM) Phase-2(Corporate Action and Reminder) | 2025-09-01 | we have already designed standard API gateway for future expansion and data dissemination. Depends on management approval | Md Kamrul Islam, Md Abdul Kader | Md. Kamruzzaman
2 | Financial Information Management in CIM | 2025-12-01 | 2 months required after receiving BRS. R & I department is preparing BRS | Md Kamrul Islam, Md Abdul Kader
3 | Online TREC Information Request from Broker houses | 2025-11-01 | Facilitate TREC users to view their information and request for update through TMS | Golam Kibria , Md Saiful Islam
4 | Shareholder Information in TMS | 2025-07-01 | Manage share holding position of TREC companies. UAT is going on and we will go live by the end of this month inshallah. | Golam Kibria , Md Saiful Islam
5 | Meeting Management System | 2025-09-01 | Meeting memo and minutes upload option , Designing dynamic search with different parameter. Depends on management approval | Md. Kamruzzaman, Mahsin Kabir
6 | Development of Smart dashboard for HR module in DSE-ERP | 2025-10-01 | Custom dashborad for HRD | Md. Kamruzzaman, Mahsin Kabir
7 | Development Intern Application management in DSE-ERP | 2025-09-01 | Automation intern on boarding in DSE-ERP | Md. Kamruzzaman, Mahsin Kabir
8 | Modification of Loan Approval Process | 2025-11-01 | To restrict specific employee from providing loan | Md. Kamruzzaman, Mahsin Kabir
9 | Customization of rights offer for subscription of the preference shares of Renata PLC in ESS | 2025-09-01 | ESS application needs to be modified by september as per BSEC order | Md Kamrul Islam, Md Abdul Kader
10 | Online Registration and Renewal Portal for Stock-Broker, Stock-Dealer, and Authorized Representative Certificates | 2026-02-01 | Need detail anaylis | Golam Kibria , Md Saiful Islam
11 | DSE Vehicle Requisition-automation in DSE-ERP |  |  | Md Mahsin Kabir
12 | Eliminitaion of suspention of securities on Record date in CNS |  | Need detail anaylis | Md. Abdur Kader, Golam Kibria
13 | Migrate the Action Management Module from DSS to ERP and Integrating it with Meeting Management.