## Modules
Sl No | Module Name | Days= Full Working Day | Remarks
1 | TREC Management | 14
2 | Broker Management | 12
3 | Dealer Management | 12
4 | TREC Personnel | 3
5 | TREC Holder Representatives | 5
6 | Compliance Authoritiess | 5
7 | TREC CAMALCO | 5
8 | TREC Power Of Attorneys | 5
9 | Authorize Representatives | 12
10 | Offices | 20
11 | Offices Network Info | 4
12 | Workstations | 18
13 | Dual TREC | 3
14 | TREC Auditor | 3
15 | TREC Parent Company | 3
16 | TREC Documents | 5
17 | TREC Capital | 3
18 | Dashboard | 6
19 | Reports | 30
20 | User Module | 16
21 | Role Based Access Control | 16
22 | Audit Trail | 20
23 | Architechture Design | 50
24 | Data migration (tools,validation,reconciling etc.) | 10
25 | UAT (internal) | 3
26 | Mock (all participants) | 3
27 | UAT, Mock and Live Server Configuration and Deployment | 3
289

## Featues
Sl No | Module Name | Features | Days= Full Working Day | Remarks
1 | TREC Information | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status History | 1
|  | Status Change | 2
|  | Status Edit | 2
|  | Name History | 1
|  | Name Change | 1
|  | Name Edit | 1
|  | Code History | 1
|  | Code Change | 1
|  | Code Edit | 1
2 | Broker License | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status History | 1
|  | Status Change | 2
|  | Status Edit | 2
|  | Renew History | 1
|  | Renew | 1
|  | Renew Edit | 1
|  | License Expire Reminders | 1
3 | Dealer License | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status History | 1
|  | Status Change | 2
|  | Status Edit | 2
|  | Renew History | 1
|  | Renew | 1
|  | Renew Edit | 1
|  | License Expire Reminders | 1
4 | TREC Personnel | List | 1
|  | Add | 1
|  | Edit | 1
5 | TREC Holder Representatives | List | 1
|  | Add | 1
|  | Change History | 1
|  | Change History > Change | 1
|  | Change History > Edit | 1
6 | Compliance Authorities | List | 1
|  | Add | 1
|  | Change History | 1
|  | Change History > Change | 1
|  | Change History > Edit | 1
7 | TREC CAMALCO | List | 1
|  | Add | 1
|  | Change History | 1
|  | Change History > Change | 1
|  | Change History > Edit | 1
8 | TREC Power Of Attorneys | List | 1
|  | Add | 1
|  | Change History | 1
|  | Change History > Change | 1
|  | Change History > Edit | 1
9 | Authorize Representatives | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status History | 1
|  | Status History Edit | 2
|  | Status Change | 2
|  | Renew History | 1
|  | Renew History Edit | 1
|  | Renew | 1
|  | License Expire Reminders | 1
10 | Offices | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status Change History | 1
|  | Status Change History Edit | 2
|  | Status Change | 2
|  | Type History | 1
|  | Type History Edit | 1
|  | Type Change | 1
|  | Shift History | 1
|  | Shift History Edit | 1
|  | Shift Office | 1
|  | Incharge History | 1
|  | Incharge History Edit | 1
|  | Incharge Change | 1
|  | Compliance Officer History | 1
|  | Compliance Officer History Edit | 1
|  | Compliance Officer Change | 1
11 | Offices Network Info | List | 1
|  | Network History | 1
|  | Network Info Add | 1
|  | Network Info Edit | 1
12 | Workstations | List | 1
|  | Add | 1
|  | Edit | 1
|  | Status Change History | 1
|  | Status Change History Edit | 2
|  | Status Change | 2
|  | Workstation Office Mapping history | 1
|  | Workstation Office Mapping | 2
|  | Workstation Office Edit | 2
|  | AR mapping and history | 1
|  | Workstation AR Mapping | 2
|  | Workstation AR Edit | 2
13 | Dual TREC | List | 1
|  | Dual TREC Add | 1
|  | Dual TREC Edit | 1
14 | TREC Auditor | List | 1
|  | Network Info Add | 1
|  | Network Info Edit | 1
15 | TREC Parent Company | List | 1
|  | TREC Parent Company Add | 1
|  | TREC Parent Company Edit | 1
16 | TREC Documents | List | 1
|  | TREC Documents Add | 2
|  | TREC Documents Edit | 2
17 | TREC Capital | List | 1
|  | TREC Capital Add | 1
|  | TREC Capital Edit | 1
18 | Dashboard | Dynamic Dashboard based on user category | 6
19 | Reports |  | 30
20 | User Module | Login | 2
|  | Logout | 2
|  | Change Password | 1
|  | Forgot Password | 2
|  | Change Email | 1
|  | System Param Configuration | 2
|  | User Param Configuration | 2
|  | Password Lock/Open | 2
|  | 2 Factor Authentication using Email OTP | 2
21 | Role Based Access Control | Role | 2
|  | Menu | 2
|  | Role Menus | 2
|  | User Profile with Approval | 2
|  | User Profile Change after Approval | 2
|  | User Info with Approval | 2
|  | User Info Change after Approval | 2
|  | User Role/Role Based Access | 2
22 | Audit Trail | Architecture for Audit Trail | 4
|  | Implement audit trail during data modification | 12
|  | View the User login history | 2
|  | View the User login Activity | 2
23 | Architechture Design | Software Architecture Design | 20
|  | Database Schema Design | 15
|  | Frontend Theme Design | 15
24 | Data migration | tools,validation,reconciling etc. | 10
25 | UAT (internal) | App Server Configuration | 1
|  | File Server Configuration | 1
|  | Database Server Configuration | 1
26 | Mock (all participants) | App Server Configuration | 1
|  | File Server Configuration | 1
|  | Database Server Configuration | 1
27 | Live | App Server Configuration | 1
|  | File Server Configuration | 1
|  | Database Server Configuration | 1
289